## Start
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Comments
1 | Define project scope | Alice | 2024-05-01 | 2024-05-03 | Completed | Scope defined in mtg.
2 | Create project schedule | Bob | 2024-05-04 | 2024-05-10 | In Progress | Awaiting stakeholder approval
3 | Resource allocation | Claire | 2024-05-05 | 2024-05-12 | Not Started
4 | Project kickoff meeting | Alice | 2024-05-13 | 2024-05-13 | Scheduled | Prepare presentation
5 | First deliverable draft | Bob | 2024-05-14 | 2024-06-01 | Not Started
6 | Client review meeting | Claire | 2024-06-02 | 2024-06-02 | Scheduled | Review all documents

## Complete
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Comments | Start Month
1 | Define project scope | Alice | 2024-05-01 | 2024-05-03 | Completed | Scope defined in mtg. | 5
2 | Create project schedule | Bob | 2024-05-04 | 2024-05-10 | In Progress | Awaiting stakeholder approval | 5
3 | Resource allocation | Claire | 2024-05-05 | 2024-05-12 | Not Started |  | 5
4 | Project kickoff meeting | Alice | 2024-05-13 | 2024-05-13 | Not Started | Prepare presentation | 5
5 | First deliverable draft | Bob | 2024-05-14 | 2024-06-01 | Not Started |  | 5
6 | Client review meeting | Claire | 2024-06-02 | 2024-06-02 | Scheduled | Review all documents | 6
7 | Project teardown meeting | Bob | 2024-05-14 | 2024-06-01 | In Progress |  | 5
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.