## Project Data
Project Name | Start Date | End Date | Actual End Date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Project Status
Magic Portal Development | 44927 | 45291 | 45245 | 200000 | 210000 | 220000 | Completed
Clown Car Integration | 44958 | 45261 | 45229 | 150000 | 145000 | 140000 | Completed
Tickling Timer Setup | 44986 | 45350 | 45306 | 180000 | 175000 | 170000 | Completed
Joke Distribution Network | 45017 | 45260 | 45219 | 120000 | 125000 | 130000 | Completed
Giggle Gas Plant | 45047 | 45291 | 45240 | 300000 | 310000 | 320000 | Completed
Mirth Manufacturing | 45078 | 45443 | 45402 | 220000 | 215000 | 210000 | Completed
Laugh Lab Construction | 45108 | 45473 | 45437 | 250000 | 255000 | 260000 | Completed
Comical Camera Setup | 45139 | 45504 | 45463 | 180000 | 185000 | 190000 | Completed
Amusement Park Design | 45170 | 45535 | 45498 | 270000 | 265000 | 260000 | Completed
Comedy Club Network | 45200 | 45565 | 45519 | 150000 | 155000 | 160000 | Completed
Merry Mall Construction | 45231 | 45596 | 45545 | 320000 | 330000 | 340000 | Completed
Prankster Park Setup | 45261 | 45626 | 45585 | 230000 | 225000 | 220000 | Completed
Laughable Lighting Project | 45292 | 45657 | 45621 | 190000 | 195000 | 200000 | Completed
Grin Garage Construction | 45323 | 45688 | 45641 | 260000 | 255000 | 250000 | Completed
Laughter Lounge Setup | 45352 | 45716 | 45667 | 300000 | 310000 | 320000 | Completed
Fun Factory Installation | 45383 | 45747 | - | 170000 | 80000 | 90000 | Ongoing
Comedy Clubhouse Setup | 45413 | 45777 | - | 200000 | 50000 | 60000 | Ongoing
Dancing Disco Development | 45444 | 45808 | - | 280000 | 20000 | 30000 | Ongoing
Trickster Theater Setup | 45474 | 45838 | - | 220000 | 40000 | 50000 | Ongoing
Humorous Hotel Design | 45505 | 45869 | - | 350000 | 0 | 0 | Not Started
Laugh Lounge Installation | 45536 | 45900 | - | 240000 | 0 | 0 | Not Started
Witty Warehouse Setup | 45566 | 45930 | - | 210000 | 0 | 0 | Not Started
Happy House Project | 45597 | 45961 | - | 300000 | 0 | 0 | Not Started
Playful Plaza Design | 45627 | 45991 | - | 270000 | 0 | 0 | Not Started
Comedy Courtyard Setup | 45658 | 46022 | - | 190000 | 0 | 0 | Not Started

## Safety Incidents
Project Name | Incident Date | Incident Type | Severity | Description
Magic Portal Development | 45061 | Slip and Fall | Medium | Worker slipped on a magic carpet.
Magic Portal Development | 45158 | Equipment Failure | Low | Magic wand malfunctioned, no injuries.
Clown Car Integration | 45117 | Electrical Shock | High | Electrician received a shock from a clown car horn.
Clown Car Integration | 45224 | Fire | High | Small fire in the balloon storage area.
Clown Car Integration | 45270 | Slip and Fall | Medium | Worker slipped on a banana peel.
Tickling Timer Setup | 45194 | Equipment Failure | Low | Timer malfunctioned during a tickling contest.
Joke Distribution Network | 45082 | Chemical Spill | Medium | Spill of fake laughing gas.
Joke Distribution Network | 45179 | Slip and Fall | Medium | Worker slipped on a rubber chicken.
Joke Distribution Network | 45245 | Prank Gone Wrong | Low | Prank phone fell off the shelf, no injuries.
Giggle Gas Plant | 45158 | Fire | High | Minor fire caused by a giggling flame.
Giggle Gas Plant | 45245 | Electrical Shock | High | Worker received a shock from a laughing generator.
Mirth Manufacturing | 45242 | Machinery Accident | High | Worker injured by a joy buzzers assembly machine.
Mirth Manufacturing | 45373 | Slip and Fall | Medium | Worker slipped on a puddle of mirth syrup.
Mirth Manufacturing | 45448 | Chemical Spill | Medium | Spill of giggle gel in the factory.
Laugh Lab Construction | 45337 | Fall from Height | High | Worker fell from a laughing ladder.
Laugh Lab Construction | 45400 | Chemical Spill | Medium | Small spill of giggle gas.
Laugh Lab Construction | 45514 | Equipment Failure | Low | Laugh detector malfunctioned, no injuries.
Comical Camera Setup | 45200 | Slip and Fall | Medium | Worker slipped on a comically large camera lens.
Comical Camera Setup | 45347 | Electrical Shock | High | Electrician shocked by a flash from a joke camera.
Comical Camera Setup | 45442 | Equipment Failure | Low | Camera tripod collapsed during setup.
Amusement Park Design | 45290 | Electrical Shock | Medium | Designer shocked by a funhouse mirror.
Amusement Park Design | 45397 | Equipment Failure | Low | Ferris wheel model collapsed, no injuries.
Amusement Park Design | 45495 | Slip and Fall | Medium | Worker slipped on roller coaster track model.
Comedy Club Network | 45306 | Equipment Failure | Low | Microphone stand fell over during setup.
Comedy Club Network | 45417 | Fire | High | Fire caused by a flaming joke book.
Comedy Club Network | 45553 | Prank Gone Wrong | Low | Whoopee cushion explosion, no injuries.
Merry Mall Construction | 45404 | Fire | High | Fire in the merry-go-round installation area.
Merry Mall Construction | 45519 | Machinery Accident | High | Worker injured by a jolly jackhammer.
Merry Mall Construction | 45606 | Slip and Fall | Medium | Worker slipped on a jolly jumper.
Prankster Park Setup | 45369 | Machinery Accident | High | Worker injured by a prank roller coaster.
Prankster Park Setup | 45498 | Slip and Fall | Medium | Worker slipped on a fake snake.
Prankster Park Setup | 45540 | Prank Gone Wrong | Low | Fake spider scare caused minor injuries.
Laughable Lighting Project | 45453 | Slip and Fall | Medium | Worker slipped on a spotlight.
Laughable Lighting Project | 45540 | Electrical Shock | High | Worker received a shock from a laughing light bulb.
Grin Garage Construction | 45498 | Chemical Spill | Medium | Small spill of grin grease.
Grin Garage Construction | 45614 | Fall from Height | High | Worker fell from a smiling scaffold.
Grin Garage Construction | 45708 | Equipment Failure | Low | Tool chest fell over, no injuries.
Laughter Lounge Setup | 45417 | Electrical Shock | High | Electrician shocked by a laugh track.
Laughter Lounge Setup | 45587 | Machinery Accident | High | Worker injured by a laughter machine.
Laughter Lounge Setup | 45667 | Slip and Fall | Medium | Worker slipped on a joy cushion.
Comedy Clubhouse Setup | 45555 | Fall from Height | High | Worker fell from a comedy stage.
Comedy Clubhouse Setup | 45675 | Slip and Fall | Medium | Worker slipped on a punchline.
Comedy Clubhouse Setup | 45759 | Electrical Shock | High | Electrician shocked by a joke sign.
Dancing Disco Development | 45583 | Machinery Accident | High | Worker injured by a disco ball.
Dancing Disco Development | 45700 | Electrical Shock | High | Worker received a shock from dance floor lighting.
Dancing Disco Development | 45797 | Overcrowding | Medium | Too many dancers on the dance floor.
Dancing Disco Development | 45843 | Music Incident | Low | Workers couldn't stop dancing to Depeche Mode.
Trickster Theater Setup | 45607 | Slip and Fall | Medium | Worker slipped on a fake banana peel on stage.
Trickster Theater Setup | 45734 | Fire | High | Small fire in the prank prop storage.
Trickster Theater Setup | 45818 | Prank Gone Wrong | Low | Water bucket prank went wrong, no injuries.
Humorous Hotel Design | 45631 | Fire | High | Fire in the design office caused by a joke candle.
Humorous Hotel Design | 45767 | Fall from Height | High | Worker fell from a comedy ladder.
Humorous Hotel Design | 45884 | Chemical Spill | Medium | Spill of hilarious cleaning fluid.
Laugh Lounge Installation | 45677 | Chemical Spill | Medium | Small spill of laughter lubricant.
Laugh Lounge Installation | 45795 | Equipment Failure | Low | Laugh track player malfunctioned, no injuries.
Laugh Lounge Installation | 45910 | Fall from Height | High | Worker fell from a laughter stage.
Witty Warehouse Setup | 45702 | Electrical Shock | High | Worker received a shock from a witty light switch.