## Project Data
Project Name | Start Date | End Date | Actual End Date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Project Status | SPI | CPI | Safety Incident Count
Magic Portal Development | 2023-01-01 | 2023-12-31 | 2023-11-15 | 200000 | 210000 | 220000 | Completed | 1.05 | 0.95455 | 2
Clown Car Integration | 2023-02-01 | 2023-12-01 | 2023-10-30 | 150000 | 145000 | 140000 | Completed | 0.96667 | 1.0357 | 3
Tickling Timer Setup | 2023-03-01 | 2024-02-28 | 2024-01-15 | 180000 | 175000 | 170000 | Completed | 0.97222 | 1.0294 | 1
Joke Distribution Network | 2023-04-01 | 2023-11-30 | 2023-10-20 | 120000 | 125000 | 130000 | Completed | 1.0417 | 0.96154 | 3
Giggle Gas Plant | 2023-05-01 | 2023-12-31 | 2023-11-10 | 300000 | 310000 | 320000 | Completed | 1.0333 | 0.96875 | 2
Mirth Manufacturing | 2023-06-01 | 2024-05-31 | 2024-04-20 | 220000 | 215000 | 210000 | Completed | 0.97727 | 1.0238 | 3
Laugh Lab Construction | 2023-07-01 | 2024-06-30 | 2024-05-25 | 250000 | 255000 | 260000 | Completed | 1.02 | 0.98077 | 3
Comical Camera Setup | 2023-08-01 | 2024-07-31 | 2024-06-20 | 180000 | 185000 | 190000 | Completed | 1.0278 | 0.97368 | 3
Amusement Park Design | 2023-09-01 | 2024-08-31 | 2024-07-25 | 270000 | 265000 | 260000 | Completed | 0.98148 | 1.0192 | 3
Comedy Club Network | 2023-10-01 | 2024-09-30 | 2024-08-15 | 150000 | 155000 | 160000 | Completed | 1.0333 | 0.96875 | 3
Merry Mall Construction | 2023-11-01 | 2024-10-31 | 2024-09-10 | 320000 | 330000 | 340000 | Completed | 1.0312 | 0.97059 | 3
Prankster Park Setup | 2023-12-01 | 2024-11-30 | 2024-10-20 | 230000 | 225000 | 220000 | Completed | 0.97826 | 1.0227 | 3
Laughable Lighting Project | 2024-01-01 | 2024-12-31 | 2024-11-25 | 190000 | 195000 | 200000 | Completed | 1.0263 | 0.975 | 2
Grin Garage Construction | 2024-02-01 | 2025-01-31 | 2024-12-15 | 260000 | 255000 | 250000 | Completed | 0.98077 | 1.02 | 3
Laughter Lounge Setup | 2024-03-01 | 2025-02-28 | 2025-01-10 | 300000 | 310000 | 320000 | Completed | 1.0333 | 0.96875 | 3
Fun Factory Installation | 2024-04-01 | 2025-03-31 | - | 170000 | 80000 | 90000 | Ongoing | 0.47059 | 0.88889 | 0
Comedy Clubhouse Setup | 2024-05-01 | 2025-04-30 | - | 200000 | 50000 | 60000 | Ongoing | 0.25 | 0.83333 | 3
Dancing Disco Development | 2024-06-01 | 2025-05-31 | - | 280000 | 20000 | 30000 | Ongoing | 0.071429 | 0.66667 | 4
Trickster Theater Setup | 2024-07-01 | 2025-06-30 | - | 220000 | 40000 | 50000 | Ongoing | 0.18182 | 0.8 | 3
Humorous Hotel Design | 2024-08-01 | 2025-07-31 | - | 350000 | 0 | 0 | Not Started | 0 | 0 | 3
Laugh Lounge Installation | 2024-09-01 | 2025-08-31 | - | 240000 | 0 | 0 | Not Started | 0 | 0 | 3
Witty Warehouse Setup | 2024-10-01 | 2025-09-30 | - | 210000 | 0 | 0 | Not Started | 0 | 0 | 1
Happy House Project | 2024-11-01 | 2025-10-31 | - | 300000 | 0 | 0 | Not Started | 0 | 0 | 0
Playful Plaza Design | 2024-12-01 | 2025-11-30 | - | 270000 | 0 | 0 | Not Started | 0 | 0 | 0
Comedy Courtyard Setup | 2025-01-01 | 2025-12-31 | - | 190000 | 0 | 0 | Not Started | 0 | 0 | 0

## Safety Incidents
Project Name | Incident Date | Incident Type | Severity | Description
Magic Portal Development | 2023-05-15 | Slip and Fall | Medium | Worker slipped on a magic carpet.
Magic Portal Development | 2023-08-20 | Equipment Failure | Low | Magic wand malfunctioned, no injuries.
Clown Car Integration | 2023-07-10 | Electrical Shock | High | Electrician received a shock from a clown car horn.
Clown Car Integration | 2023-10-25 | Fire | High | Small fire in the balloon storage area.
Clown Car Integration | 2023-12-10 | Slip and Fall | Medium | Worker slipped on a banana peel.
Tickling Timer Setup | 2023-09-25 | Equipment Failure | Low | Timer malfunctioned during a tickling contest.
Joke Distribution Network | 2023-06-05 | Chemical Spill | Medium | Spill of fake laughing gas.
Joke Distribution Network | 2023-09-10 | Slip and Fall | Medium | Worker slipped on a rubber chicken.
Joke Distribution Network | 2023-11-15 | Prank Gone Wrong | Low | Prank phone fell off the shelf, no injuries.
Giggle Gas Plant | 2023-08-20 | Fire | High | Minor fire caused by a giggling flame.
Giggle Gas Plant | 2023-11-15 | Electrical Shock | High | Worker received a shock from a laughing generator.
Mirth Manufacturing | 2023-11-12 | Machinery Accident | High | Worker injured by a joy buzzers assembly machine.
Mirth Manufacturing | 2024-03-22 | Slip and Fall | Medium | Worker slipped on a puddle of mirth syrup.
Mirth Manufacturing | 2024-06-05 | Chemical Spill | Medium | Spill of giggle gel in the factory.
Laugh Lab Construction | 2024-02-15 | Fall from Height | High | Worker fell from a laughing ladder.
Laugh Lab Construction | 2024-04-18 | Chemical Spill | Medium | Small spill of giggle gas.
Laugh Lab Construction | 2024-08-10 | Equipment Failure | Low | Laugh detector malfunctioned, no injuries.
Comical Camera Setup | 2023-10-01 | Slip and Fall | Medium | Worker slipped on a comically large camera lens.
Comical Camera Setup | 2024-02-25 | Electrical Shock | High | Electrician shocked by a flash from a joke camera.
Comical Camera Setup | 2024-05-30 | Equipment Failure | Low | Camera tripod collapsed during setup.
Amusement Park Design | 2023-12-30 | Electrical Shock | Medium | Designer shocked by a funhouse mirror.
Amusement Park Design | 2024-04-15 | Equipment Failure | Low | Ferris wheel model collapsed, no injuries.
Amusement Park Design | 2024-07-22 | Slip and Fall | Medium | Worker slipped on roller coaster track model.
Comedy Club Network | 2024-01-15 | Equipment Failure | Low | Microphone stand fell over during setup.
Comedy Club Network | 2024-05-05 | Fire | High | Fire caused by a flaming joke book.
Comedy Club Network | 2024-09-18 | Prank Gone Wrong | Low | Whoopee cushion explosion, no injuries.
Merry Mall Construction | 2024-04-22 | Fire | High | Fire in the merry-go-round installation area.
Merry Mall Construction | 2024-08-15 | Machinery Accident | High | Worker injured by a jolly jackhammer.
Merry Mall Construction | 2024-11-10 | Slip and Fall | Medium | Worker slipped on a jolly jumper.
Prankster Park Setup | 2024-03-18 | Machinery Accident | High | Worker injured by a prank roller coaster.
Prankster Park Setup | 2024-07-25 | Slip and Fall | Medium | Worker slipped on a fake snake.
Prankster Park Setup | 2024-09-05 | Prank Gone Wrong | Low | Fake spider scare caused minor injuries.
Laughable Lighting Project | 2024-06-10 | Slip and Fall | Medium | Worker slipped on a spotlight.
Laughable Lighting Project | 2024-09-05 | Electrical Shock | High | Worker received a shock from a laughing light bulb.
Grin Garage Construction | 2024-07-25 | Chemical Spill | Medium | Small spill of grin grease.
Grin Garage Construction | 2024-11-18 | Fall from Height | High | Worker fell from a smiling scaffold.
Grin Garage Construction | 2025-02-20 | Equipment Failure | Low | Tool chest fell over, no injuries.
Laughter Lounge Setup | 2024-05-05 | Electrical Shock | High | Electrician shocked by a laugh track.
Laughter Lounge Setup | 2024-10-22 | Machinery Accident | High | Worker injured by a laughter machine.
Laughter Lounge Setup | 2025-01-10 | Slip and Fall | Medium | Worker slipped on a joy cushion.
Comedy Clubhouse Setup | 2024-09-20 | Fall from Height | High | Worker fell from a comedy stage.
Comedy Clubhouse Setup | 2025-01-18 | Slip and Fall | Medium | Worker slipped on a punchline.
Comedy Clubhouse Setup | 2025-04-12 | Electrical Shock | High | Electrician shocked by a joke sign.
Dancing Disco Development | 2024-10-18 | Machinery Accident | High | Worker injured by a disco ball.
Dancing Disco Development | 2025-02-12 | Electrical Shock | High | Worker received a shock from dance floor lighting.
Dancing Disco Development | 2025-05-20 | Overcrowding | Medium | Too many dancers on the dance floor.
Dancing Disco Development | 2025-07-05 | Music Incident | Low | Workers couldn't stop dancing to Depeche Mode.
Trickster Theater Setup | 2024-11-11 | Slip and Fall | Medium | Worker slipped on a fake banana peel on stage.
Trickster Theater Setup | 2025-03-18 | Fire | High | Small fire in the prank prop storage.
Trickster Theater Setup | 2025-06-10 | Prank Gone Wrong | Low | Water bucket prank went wrong, no injuries.
Humorous Hotel Design | 2024-12-05 | Fire | High | Fire in the design office caused by a joke candle.
Humorous Hotel Design | 2025-04-20 | Fall from Height | High | Worker fell from a comedy ladder.
Humorous Hotel Design | 2025-08-15 | Chemical Spill | Medium | Spill of hilarious cleaning fluid.
Laugh Lounge Installation | 2025-01-20 | Chemical Spill | Medium | Small spill of laughter lubricant.
Laugh Lounge Installation | 2025-05-18 | Equipment Failure | Low | Laugh track player malfunctioned, no injuries.
Laugh Lounge Installation | 2025-09-10 | Fall from Height | High | Worker fell from a laughter stage.
Witty Warehouse Setup | 2025-02-14 | Electrical Shock | High | Worker received a shock from a witty light switch.

## Gantt
Start Year | 2023
End Year | 2025
|  | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
|  | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Projects | [37 empty] | Start Date | End Date | Status
Magic Portal Development | [37 empty] | 2023-01-01 | 2023-12-31 | Completed
Clown Car Integration | [37 empty] | 2023-02-01 | 2023-12-01 | Completed
Tickling Timer Setup | [37 empty] | 2023-03-01 | 2024-02-28 | Completed
Joke Distribution Network | [37 empty] | 2023-04-01 | 2023-11-30 | Completed
Giggle Gas Plant | [37 empty] | 2023-05-01 | 2023-12-31 | Completed
Mirth Manufacturing | [37 empty] | 2023-06-01 | 2024-05-31 | Completed
Laugh Lab Construction | [37 empty] | 2023-07-01 | 2024-06-30 | Completed
Comical Camera Setup | [37 empty] | 2023-08-01 | 2024-07-31 | Completed
Amusement Park Design | [37 empty] | 2023-09-01 | 2024-08-31 | Completed
Comedy Club Network | [37 empty] | 2023-10-01 | 2024-09-30 | Completed
Merry Mall Construction | [37 empty] | 2023-11-01 | 2024-10-31 | Completed
Prankster Park Setup | [37 empty] | 2023-12-01 | 2024-11-30 | Completed
Laughable Lighting Project | [37 empty] | 2024-01-01 | 2024-12-31 | Completed
Grin Garage Construction | [37 empty] | 2024-02-01 | 2025-01-31 | Completed
Laughter Lounge Setup | [37 empty] | 2024-03-01 | 2025-02-28 | Completed
Fun Factory Installation | [37 empty] | 2024-04-01 | 2025-03-31 | Ongoing
Comedy Clubhouse Setup | [37 empty] | 2024-05-01 | 2025-04-30 | Ongoing
Dancing Disco Development | [37 empty] | 2024-06-01 | 2025-05-31 | Ongoing
Trickster Theater Setup | [37 empty] | 2024-07-01 | 2025-06-30 | Ongoing
Humorous Hotel Design | [37 empty] | 2024-08-01 | 2025-07-31 | Not Started
Laugh Lounge Installation | [37 empty] | 2024-09-01 | 2025-08-31 | Not Started
Witty Warehouse Setup | [37 empty] | 2024-10-01 | 2025-09-30 | Not Started
Happy House Project | [37 empty] | 2024-11-01 | 2025-10-31 | Not Started
Playful Plaza Design | [37 empty] | 2024-12-01 | 2025-11-30 | Not Started
Comedy Courtyard Setup | [37 empty] | 2025-01-01 | 2025-12-31 | Not Started
Formulas:
Start Date = ProjectData[Start Date]
End Date = ProjectData[End Date]

## Pivot Table
Count of Project Name | Column Labels
Row Labels | High | Low | Medium | Grand Total
Amusement Park Design |  | 1 | 2 | 3
Clown Car Integration | 2 |  | 1 | 3
Comedy Club Network | 1 | 2 |  | 3
Comedy Clubhouse Setup | 2 |  | 1 | 3
Comical Camera Setup | 1 | 1 | 1 | 3
Dancing Disco Development | 2 | 1 | 1 | 4
Giggle Gas Plant | 2 |  |  | 2
Grin Garage Construction | 1 | 1 | 1 | 3
Humorous Hotel Design | 2 |  | 1 | 3
Joke Distribution Network |  | 1 | 2 | 3
Laugh Lab Construction | 1 | 1 | 1 | 3
Laugh Lounge Installation | 1 | 1 | 1 | 3
Laughable Lighting Project | 1 |  | 1 | 2
Laughter Lounge Setup | 2 |  | 1 | 3
Magic Portal Development |  | 1 | 1 | 2
Merry Mall Construction | 2 |  | 1 | 3
Mirth Manufacturing | 1 |  | 2 | 3
Prankster Park Setup | 1 | 1 | 1 | 3
Tickling Timer Setup |  | 1 |  | 1
Trickster Theater Setup | 1 | 1 | 1 | 3
Witty Warehouse Setup | 1 |  |  | 1
Grand Total | 24 | 13 | 20 | 57