## Project Data
Project Name | Start Date | End Date | Actual End Date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Project Status | SPI | CPI | Safety Incident Count
Magic Portal Development | 2023-01-01 | 2023-12-31 | 2023-11-15 | 200000 | 210000 | 220000 | Completed | 1.05 | 0.95455 | 2
Clown Car Integration | 2023-02-01 | 2023-12-01 | 2023-10-30 | 150000 | 145000 | 140000 | Completed | 0.96667 | 1.0357 | 3
Tickling Timer Setup | 2023-03-01 | 2024-02-28 | 2024-01-15 | 180000 | 175000 | 170000 | Completed | 0.97222 | 1.0294 | 1
Joke Distribution Network | 2023-04-01 | 2023-11-30 | 2023-10-20 | 120000 | 125000 | 130000 | Completed | 1.0417 | 0.96154 | 3
Giggle Gas Plant | 2023-05-01 | 2023-12-31 | 2023-11-10 | 300000 | 310000 | 320000 | Completed | 1.0333 | 0.96875 | 2
Mirth Manufacturing | 2023-06-01 | 2024-05-31 | 2024-04-20 | 220000 | 215000 | 210000 | Completed | 0.97727 | 1.0238 | 3
Laugh Lab Construction | 2023-07-01 | 2024-06-30 | 2024-05-25 | 250000 | 255000 | 260000 | Completed | 1.02 | 0.98077 | 3
Comical Camera Setup | 2023-08-01 | 2024-07-31 | 2024-06-20 | 180000 | 185000 | 190000 | Completed | 1.0278 | 0.97368 | 3
Amusement Park Design | 2023-09-01 | 2024-08-31 | 2024-07-25 | 270000 | 265000 | 260000 | Completed | 0.98148 | 1.0192 | 3
Comedy Club Network | 2023-10-01 | 2024-09-30 | 2024-08-15 | 150000 | 155000 | 160000 | Completed | 1.0333 | 0.96875 | 3
Merry Mall Construction | 2023-11-01 | 2024-10-31 | 2024-09-10 | 320000 | 330000 | 340000 | Completed | 1.0312 | 0.97059 | 3
Prankster Park Setup | 2023-12-01 | 2024-11-30 | 2024-10-20 | 230000 | 225000 | 220000 | Completed | 0.97826 | 1.0227 | 3
Laughable Lighting Project | 2024-01-01 | 2024-12-31 | 2024-11-25 | 190000 | 195000 | 200000 | Completed | 1.0263 | 0.975 | 2
Grin Garage Construction | 2024-02-01 | 2025-01-31 | 2024-12-15 | 260000 | 255000 | 250000 | Completed | 0.98077 | 1.02 | 3
Laughter Lounge Setup | 2024-03-01 | 2025-02-28 | 2025-01-10 | 300000 | 310000 | 320000 | Completed | 1.0333 | 0.96875 | 3
Fun Factory Installation | 2024-04-01 | 2025-03-31 | - | 170000 | 80000 | 90000 | Ongoing | 0.47059 | 0.88889 | 0
Comedy Clubhouse Setup | 2024-05-01 | 2025-04-30 | - | 200000 | 50000 | 60000 | Ongoing | 0.25 | 0.83333 | 3
Dancing Disco Development | 2024-06-01 | 2025-05-31 | - | 280000 | 20000 | 30000 | Ongoing | 0.071429 | 0.66667 | 4
Trickster Theater Setup | 2024-07-01 | 2025-06-30 | - | 220000 | 40000 | 50000 | Ongoing | 0.18182 | 0.8 | 3
Humorous Hotel Design | 2024-08-01 | 2025-07-31 | - | 350000 | 0 | 0 | Not Started | 0 | 0 | 3
Laugh Lounge Installation | 2024-09-01 | 2025-08-31 | - | 240000 | 0 | 0 | Not Started | 0 | 0 | 3
Witty Warehouse Setup | 2024-10-01 | 2025-09-30 | - | 210000 | 0 | 0 | Not Started | 0 | 0 | 1
Happy House Project | 2024-11-01 | 2025-10-31 | - | 300000 | 0 | 0 | Not Started | 0 | 0 | 0
Playful Plaza Design | 2024-12-01 | 2025-11-30 | - | 270000 | 0 | 0 | Not Started | 0 | 0 | 0
Comedy Courtyard Setup | 2025-01-01 | 2025-12-31 | - | 190000 | 0 | 0 | Not Started | 0 | 0 | 0

## Safety Incidents
Project Name | Incident Date | Incident Type | Severity | Description
Magic Portal Development | 2023-05-15 | Slip and Fall | Medium | Worker slipped on a magic carpet.
Magic Portal Development | 2023-08-20 | Equipment Failure | Low | Magic wand malfunctioned, no injuries.
Clown Car Integration | 2023-07-10 | Electrical Shock | High | Electrician received a shock from a clown car horn.
Clown Car Integration | 2023-10-25 | Fire | High | Small fire in the balloon storage area.
Clown Car Integration | 2023-12-10 | Slip and Fall | Medium | Worker slipped on a banana peel.
Tickling Timer Setup | 2023-09-25 | Equipment Failure | Low | Timer malfunctioned during a tickling contest.
Joke Distribution Network | 2023-06-05 | Chemical Spill | Medium | Spill of fake laughing gas.
Joke Distribution Network | 2023-09-10 | Slip and Fall | Medium | Worker slipped on a rubber chicken.
Joke Distribution Network | 2023-11-15 | Prank Gone Wrong | Low | Prank phone fell off the shelf, no injuries.
Giggle Gas Plant | 2023-08-20 | Fire | High | Minor fire caused by a giggling flame.
Giggle Gas Plant | 2023-11-15 | Electrical Shock | High | Worker received a shock from a laughing generator.
Mirth Manufacturing | 2023-11-12 | Machinery Accident | High | Worker injured by a joy buzzers assembly machine.
Mirth Manufacturing | 2024-03-22 | Slip and Fall | Medium | Worker slipped on a puddle of mirth syrup.
Mirth Manufacturing | 2024-06-05 | Chemical Spill | Medium | Spill of giggle gel in the factory.
Laugh Lab Construction | 2024-02-15 | Fall from Height | High | Worker fell from a laughing ladder.
Laugh Lab Construction | 2024-04-18 | Chemical Spill | Medium | Small spill of giggle gas.
Laugh Lab Construction | 2024-08-10 | Equipment Failure | Low | Laugh detector malfunctioned, no injuries.
Comical Camera Setup | 2023-10-01 | Slip and Fall | Medium | Worker slipped on a comically large camera lens.
Comical Camera Setup | 2024-02-25 | Electrical Shock | High | Electrician shocked by a flash from a joke camera.
Comical Camera Setup | 2024-05-30 | Equipment Failure | Low | Camera tripod collapsed during setup.
Amusement Park Design | 2023-12-30 | Electrical Shock | Medium | Designer shocked by a funhouse mirror.
Amusement Park Design | 2024-04-15 | Equipment Failure | Low | Ferris wheel model collapsed, no injuries.
Amusement Park Design | 2024-07-22 | Slip and Fall | Medium | Worker slipped on roller coaster track model.
Comedy Club Network | 2024-01-15 | Equipment Failure | Low | Microphone stand fell over during setup.
Comedy Club Network | 2024-05-05 | Fire | High | Fire caused by a flaming joke book.
Comedy Club Network | 2024-09-18 | Prank Gone Wrong | Low | Whoopee cushion explosion, no injuries.
Merry Mall Construction | 2024-04-22 | Fire | High | Fire in the merry-go-round installation area.
Merry Mall Construction | 2024-08-15 | Machinery Accident | High | Worker injured by a jolly jackhammer.
Merry Mall Construction | 2024-11-10 | Slip and Fall | Medium | Worker slipped on a jolly jumper.
Prankster Park Setup | 2024-03-18 | Machinery Accident | High | Worker injured by a prank roller coaster.
Prankster Park Setup | 2024-07-25 | Slip and Fall | Medium | Worker slipped on a fake snake.
Prankster Park Setup | 2024-09-05 | Prank Gone Wrong | Low | Fake spider scare caused minor injuries.
Laughable Lighting Project | 2024-06-10 | Slip and Fall | Medium | Worker slipped on a spotlight.
Laughable Lighting Project | 2024-09-05 | Electrical Shock | High | Worker received a shock from a laughing light bulb.
Grin Garage Construction | 2024-07-25 | Chemical Spill | Medium | Small spill of grin grease.
Grin Garage Construction | 2024-11-18 | Fall from Height | High | Worker fell from a smiling scaffold.
Grin Garage Construction | 2025-02-20 | Equipment Failure | Low | Tool chest fell over, no injuries.
Laughter Lounge Setup | 2024-05-05 | Electrical Shock | High | Electrician shocked by a laugh track.
Laughter Lounge Setup | 2024-10-22 | Machinery Accident | High | Worker injured by a laughter machine.
Laughter Lounge Setup | 2025-01-10 | Slip and Fall | Medium | Worker slipped on a joy cushion.
Comedy Clubhouse Setup | 2024-09-20 | Fall from Height | High | Worker fell from a comedy stage.
Comedy Clubhouse Setup | 2025-01-18 | Slip and Fall | Medium | Worker slipped on a punchline.
Comedy Clubhouse Setup | 2025-04-12 | Electrical Shock | High | Electrician shocked by a joke sign.
Dancing Disco Development | 2024-10-18 | Machinery Accident | High | Worker injured by a disco ball.
Dancing Disco Development | 2025-02-12 | Electrical Shock | High | Worker received a shock from dance floor lighting.
Dancing Disco Development | 2025-05-20 | Overcrowding | Medium | Too many dancers on the dance floor.
Dancing Disco Development | 2025-07-05 | Music Incident | Low | Workers couldn't stop dancing to Depeche Mode.
Trickster Theater Setup | 2024-11-11 | Slip and Fall | Medium | Worker slipped on a fake banana peel on stage.
Trickster Theater Setup | 2025-03-18 | Fire | High | Small fire in the prank prop storage.
Trickster Theater Setup | 2025-06-10 | Prank Gone Wrong | Low | Water bucket prank went wrong, no injuries.
Humorous Hotel Design | 2024-12-05 | Fire | High | Fire in the design office caused by a joke candle.
Humorous Hotel Design | 2025-04-20 | Fall from Height | High | Worker fell from a comedy ladder.
Humorous Hotel Design | 2025-08-15 | Chemical Spill | Medium | Spill of hilarious cleaning fluid.
Laugh Lounge Installation | 2025-01-20 | Chemical Spill | Medium | Small spill of laughter lubricant.
Laugh Lounge Installation | 2025-05-18 | Equipment Failure | Low | Laugh track player malfunctioned, no injuries.
Laugh Lounge Installation | 2025-09-10 | Fall from Height | High | Worker fell from a laughter stage.
Witty Warehouse Setup | 2025-02-14 | Electrical Shock | High | Worker received a shock from a witty light switch.

## Gantt
|  |  | AVG SPI | [6 empty] | AVG CPI | [6 empty] | Total Safety Count
Start Year | 2023 |  | 0.6451 | [6 empty] | 0.72249 | [6 empty] | 57
End Year | 2025
Scenario
|  | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
|  | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | Original |  |  | Scenario
Projects | [37 empty] | Start Date | End Date | Status | Start Date | End Date | Status
Magic Portal Development |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-01-01 | 2023-12-31 | Completed | 2023-01-01 | 2023-12-31 | Completed
Clown Car Integration |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-02-01 | 2023-12-01 | Completed | 2023-04-01 | 2023-12-01 | Ongoing
Tickling Timer Setup |  | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-03-01 | 2024-02-28 | Completed | 2023-03-01 | 2024-02-28 | Completed
Joke Distribution Network |  | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-04-01 | 2023-11-30 | Completed | 2023-04-01 | 2023-11-30 | Completed
Giggle Gas Plant |  | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-01 | 2023-12-31 | Completed | 2023-05-01 | 2023-12-31 | Ongoing
Mirth Manufacturing |  | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-06-01 | 2024-05-31 | Completed | 2023-06-01 | 2024-05-31 | Completed
Laugh Lab Construction |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-07-01 | 2024-06-30 | Completed | 2023-07-01 | 2024-06-30 | Completed
Comical Camera Setup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-08-01 | 2024-07-31 | Completed | 2023-08-01 | 2024-07-31 | Completed
Amusement Park Design |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-01 | 2024-08-31 | Completed | 2023-09-01 | 2024-08-31 | Completed
Comedy Club Network |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-10-01 | 2024-09-30 | Completed | 2023-10-01 | 2024-09-30 | Completed
Merry Mall Construction |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-11-01 | 2024-10-31 | Completed | 2023-11-01 | 2024-10-31 | Not Started
Prankster Park Setup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-01 | 2024-11-30 | Completed | 2023-12-01 | 2024-11-30 | Completed
Laughable Lighting Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-01 | 2024-12-31 | Completed | 2024-01-01 | 2024-12-31 | Completed
Grin Garage Construction |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-01 | 2025-01-31 | Completed | 2024-02-01 | 2025-01-31 | Completed
Laughter Lounge Setup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-01 | 2025-02-28 | Completed | 2024-03-01 | 2025-02-28 | Completed
Fun Factory Installation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-01 | 2025-03-31 | Ongoing | 2024-04-01 | 2025-03-31 | Ongoing
Comedy Clubhouse Setup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-01 | 2025-04-30 | Ongoing | 2024-05-01 | 2025-04-30 | Ongoing
Dancing Disco Development |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-01 | 2025-05-31 | Ongoing | 2024-06-01 | 2025-05-31 | Ongoing
Trickster Theater Setup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-01 | 2025-06-30 | Ongoing | 2024-07-01 | 2025-06-30 | Ongoing
Humorous Hotel Design |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2024-08-01 | 2025-07-31 | Not Started | 2024-08-01 | 2025-07-31 | Not Started
Laugh Lounge Installation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2024-09-01 | 2025-08-31 | Not Started | 2024-09-01 | 2025-08-31 | Not Started
Witty Warehouse Setup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2024-10-01 | 2025-09-30 | Not Started | 2024-10-01 | 2025-09-30 | Not Started
Happy House Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2024-11-01 | 2025-10-31 | Not Started | 2024-11-01 | 2025-10-31 | Not Started
Playful Plaza Design |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2024-12-01 | 2025-11-30 | Not Started | 2024-12-01 | 2025-11-30 | Not Started
Comedy Courtyard Setup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2025-01-01 | 2025-12-31 | Not Started | 2025-01-01 | 2025-12-31 | Not Started
|  | 3 | 3 | 6 | 11 | 13 | 16 | 19 | 22 | 25 | 28 | 29 | 29 | 25 | 28 | 28 | 30 | 32 | 31 | 30 | 28 | 26 | 24 | 24 | 22 | 20 | 17 | 14 | 12 | 10 | 8 | 6 | 5 | 4 | 3 | 2 | 1
Formulas:
Start Date = ProjectData[Start Date]
End Date = ProjectData[End Date]

## Pivot Table
Count of Project Name | Column Labels
Row Labels | Medium | Grand Total
Grin Garage Construction | 1 | 1
Laugh Lab Construction | 1 | 1
Laugh Lounge Installation | 1 | 1
Mirth Manufacturing | 1 | 1
Grand Total | 4 | 4
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.